## Sheet1
# | ISSUE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
1 | Web security(Request bean already in creation,server not started) | High | 2022-12-12 | Ritesh | 2022-12-14 | Ritesh
2 | Roles For 2 staffs | Medium | 2022-12-12 | Ritesh | 2022-12-13 | Ritesh
3 | Manager to edit | Low | 2022-12-12 | Ritesh | 2022-12-13 | Ritesh
4 | Add to cart | Medium | 2022-12-12 | Nuthan | 2022-12-14 | Nuthan
5 | The Order Details Are Not Storing | Medium | 2022-12-12 | Nuthan | 2022-12-15 | Nuthan
6 | Validation Gmail format | Low | 2022-12-12 | Sanjay | 2022-12-13 | Sanjay
7 | Handle trimming spaces | Low | 2022-12-12 | Ritesh | 2022-12-13 | Ritesh
8 | Order date mandatory to store in DB | Medium | 2022-12-12 | Pramod | 2022-12-14 | Pramod
9 | Bill was not working according to the customer particular | High | 2022-12-13 | Megahana | 2022-12-15 | Megahana
10 | Cart amount should change according to the values | High | 2022-12-13 | Archith | 2022-12-14 | Archith
11 | Validation Error Messages | Medium | 12-13-2022 | Sanjay | 12-15-2022 | Sanjay
12 | Remove Cart From Session | Low | 2022-12-12 | Archith | 12-15-2022 | Archith
13 | Pagination Result | Low | 12-13-2022 | Megahana | 12-14-2022 | Megahana
14` | Testing Products | Low | 12-13-2022 | Pramod | 12-15-2022 | Pramod